## Sheet1
Cisco Team 3- Project Gantt Timeline
Detailed task ownership/status is maintained in Trello; dates are planning targets and may be refined between sprints. Total Project Duration: Sep 29- Dec 4th - Around 9 Weeks, 8 Weeks technical, 1 Week Final Preparation
WBS # | Work / Milestone | Primary Responsibility | Start | Target Finish | Duration (days) | Dependencies (Predecessor WBS #) | Sprint / Type | time axis 2026-09-29 to 2026-12-13
1.0 | SPRINT 1- Project Readiness, Design & Network Foundation |  | 2026-09-29 | 2026-10-12 | 14 |  | Sprint | bar: 2026-09-29 to 2026-10-12
1.1 | US-01 Standardized Network Architecture | Ben | 2026-09-29 | 2026-10-05 | 7 |  | Sprint 1 | bar: 2026-09-29 to 2026-10-09
1.2 | US-02 Consistent Network Addressing | Ben | 2026-09-29 | 2026-10-05 | 7 | 1.1 | Sprint 1 | bar: 2026-09-29 to 2026-10-05
1.3 | US-16 Consistent Network Build Standard (continues through Sprint 5) | Muhammad/Larose | 2026-10-01 | 2026-12-01 | 62 | 1.1, 1.2 | S1-S5 | bar: 2026-10-01 to 2026-12-01
1.4 | US-12 Verified Network Requirements (continues through Sprint 5) | Ben | 2026-09-29 | 2026-12-01 | 64 | 1.3 | S1-S5 | bar: 2026-10-01 to 2026-12-01
1.5 | US-03 VLANs | Matthews | 2026-10-05 | 2026-10-10 | 6 | 1.2 | Sprint 1 | bar: 2026-10-05 to 2026-10-10
1.6 | US-04 VLAN Connectivity Across Switches | Matthews | 2026-10-05 | 2026-10-10 | 6 | 1.5 | Sprint 1 | bar: 2026-10-05 to 2026-10-10
1.7 | US-05 Inter-VLAN Routing | Ben | 2026-10-08 | 2026-10-12 | 5 | 1.5, 1.6 | Sprint 1 | bar: 2026-10-08 to 2026-10-12
1.8 | US-06 Routed Network Connectivity | Matthews | 2026-10-08 | 2026-10-12 | 5 | 1.7 | Sprint 1 | bar: 2026-10-08 to 2026-10-12
1.9 | Testing / QA / Evidence / Review / Buffer | Team | 2026-10-09 | 2026-10-12 | 4 | 1.5–1.8 | Sprint 1 | bar: 2026-10-09 to 2026-10-12
1.10 | PM Progress Report 1 / Evidence Checkpoint | Ben / Team | 2026-10-08 | 2026-10-08 | 1 |  | Milestone | bar: 2026-10-08
2.0 | SPRINT 2- Centralized Services & Administrative Authentication |  | 2026-10-13 | 2026-10-26 | 14 |  | Sprint | bar: 2026-10-13 to 2026-10-26
2.1 | US-09 Centralized DHCP Service | Muhammad | 2026-10-13 | 2026-10-20 | 8 | 1.7 | Sprint 2 | bar: 2026-10-13 to 2026-10-20
2.2 | US-10 Centralized DNS Service | Muhammad | 2026-10-13 | 2026-10-20 | 8 | 1.7 | Sprint 2 | bar: 2026-10-13 to 2026-10-20
2.3 | US-13 Centralized NTP Service | Muhammad | 2026-10-13 | 2026-10-20 | 8 | 1.7 | Sprint 2 | bar: 2026-10-13 to 2026-10-20
2.4 | US-24 Automatic Network Configuration | Ben | 2026-10-15 | 2026-10-22 | 8 | 2.1 | Sprint 2 | bar: 2026-10-15 to 2026-10-22
2.5 | US-25 Internal Resource Name Resolution | Larose | 2026-10-15 | 2026-10-22 | 8 | 2.2 | Sprint 2 | bar: 2026-10-15 to 2026-10-22
2.6 | US-07 Central Admin Authentication | Muhammad | 2026-10-19 | 2026-10-25 | 7 | 2.1, 2.2 | Sprint 2 | bar: 2026-10-19 to 2026-10-25
2.7 | US-08 Secure Remote Administration | Muhammad | 2026-10-19 | 2026-10-25 | 7 | 2.6 | Sprint 2 | bar: 2026-10-19 to 2026-10-25
2.8 | Testing / QA / Evidence / Review / Buffer | Team | 2026-10-20 | 2026-10-26 | 7 | 2.1–2.7 | Sprint 2 | bar: 2026-10-20 to 2026-10-26
2.9 | PM Progress Report 2 / Evidence Checkpoint | Ben / Team | 2026-10-22 | 2026-10-22 | 1 |  | Milestone | bar: 2026-10-22
3.0 | SPRINT 3- Access Control, External Connectivity, Monitoring, Wireless & Midterm MVP |  | 2026-10-27 | 2026-11-09 | 14 |  | Sprint | bar: 2026-10-27 to 2026-11-09
3.1 | US-18 Network Access Control | Larose | 2026-10-27 | 2026-11-02 | 7 | 1.5–1.8 | Sprint 3 | bar: 2026-10-27 to 2026-11-02
3.2 | US-14 Centralized Syslog Service | Muhammad | 2026-10-27 | 2026-11-02 | 7 | 2.3 | Sprint 3 | bar: 2026-10-27 to 2026-11-02
3.3 | US-21 Port Security | Matthews | 2026-10-27 | 2026-11-01 | 6 | 1.3 | Sprint 3 | bar: 2026-10-27 to 2026-11-01
3.4 | US-22 Unused-Port Protection | Matthews | 2026-10-27 | 2026-11-01 | 6 | 1.3 | Sprint 3 | bar: 2026-10-27 to 2026-11-01
3.5 | US-19 ACL and Network-Service Integration | Larose | 2026-10-28 | 2026-11-03 | 7 | 3.1, 2.1, 2.2, 2.6 | Sprint 3 | bar: 2026-10-28 to 2026-11-03
3.6 | US-26 External Resource Access | Ben | 2026-10-28 | 2026-11-03 | 7 | 3.1 | Sprint 3 | bar: 2026-10-28 to 2026-11-03
3.7 | US-23 Access-Layer Switching Protection | Matthews | 2026-10-28 | 2026-11-02 | 6 | 1.3 | Sprint 3 | bar: 2026-10-28 to 2026-11-02
3.8 | US-20 Secure Wireless Access | Larose | 2026-10-29 | 2026-11-04 | 7 | 2.6, 2.1 | Sprint 3 | bar: 2026-10-29 to 2026-11-04
3.9 | US-27 Wireless Employee Connectivity | Muhammad | 2026-10-29 | 2026-11-04 | 7 | 3.8 | Sprint 3 | bar: 2026-10-29 to 2026-11-04
3.10 | US-28 Time-Synchronized Syslog | Muhammad | 2026-10-30 | 2026-11-04 | 6 | 2.3, 3.2 | Sprint 3 | bar: 2026-10-30 to 2026-11-04
3.11 | MVP Testing / QA / Evidence / Review / Buffer | Team | 2026-11-04 | 2026-11-09 | 6 | 3.1–3.10 | Sprint 3 | bar: 2026-11-04 to 2026-11-09
3.12 | PM Progress Report 3 / Evidence Checkpoint | Ben / Team | 2026-11-05 | 2026-11-05 | 1 |  | Milestone | bar: 2026-11-05
3.13 | IT491 Midterm MVP | Team | 2026-11-08 | 2026-11-08 | 1 | 3.11 | Milestone | bar: 2026-11-08
4.0 | SPRINT 4- Integration, Induced-Failure Testing, Non-Author Audit & Final Delivery |  | 2026-11-10 | 2026-11-23 | 14 |  | Sprint | bar: 2026-11-10 to 2026-11-23
4.1 | US-11 Integrated Network Operation | Ben | 2026-11-10 | 2026-11-18 | 9 | 3.1–3.10 | Sprint 4 | bar: 2026-11-10 to 2026-11-18
4.2 | US-32 Integration Conflict Documentation | Ben | 2026-11-10 | 2026-11-17 | 8 | 4.1 | Sprint 4 | bar: 2026-11-10 to 2026-11-17
4.3 | US-33 Protection of Sensitive Business Information | Larose | 2026-11-11 | 2026-11-17 | 7 | 3.1 | Sprint 4 | bar: 2026-11-11 to 2026-11-17
4.4 | US-34 Reliable Business-Supporting Network Operation | Matthews | 2026-11-11 | 2026-11-17 | 7 | 4.1 | Sprint 4 | bar: 2026-11-11 to 2026-11-17
4.5 | US-31 Network Troubleshooting Documentation | Matthews | 2026-11-12 | 2026-11-18 | 7 | 4.1 | Sprint 4 | bar: 2026-11-12 to 2026-11-18
4.6 | US-15 Network Audit | Larose | 2026-11-12 | 2026-11-18 | 7 | 1.3 | Sprint 4 | bar: 2026-11-12 to 2026-11-18
4.7 | US-29 ACL Dependency Troubleshooting | Larose | 2026-11-13 | 2026-11-18 | 6 | 3.1, 3.5 | Sprint 4 | bar: 2026-11-13 to 2026-11-18
4.8 | US-30 NTP Failure Troubleshooting | Muhammad | 2026-11-13 | 2026-11-18 | 6 | 2.3, 3.10 | Sprint 4 | bar: 2026-11-13 to 2026-11-18
4.9 | US-17 Verifiable Project Completion | Ben | 2026-11-14 | 2026-11-19 | 6 | 4.1–4.8 | Sprint 4 | bar: 2026-11-14 to 2026-11-19
4.10 | US-35 Verifiable Network Protection | Larose | 2026-11-14 | 2026-11-19 | 6 | 3.1, 3.3, 3.4, 3.7 | Sprint 4 | bar: 2026-11-14 to 2026-11-19
4.11 | Testing / QA / Evidence / Review / Buffer | Team | 2026-11-18 | 2026-11-23 | 6 | 4.1–4.10 | Sprint 4 | bar: 2026-11-18 to 2026-11-23
4.12 | PM Progress Report 4 / Evidence Checkpoint | Ben / Team | 2026-11-19 | 2026-11-19 | 1 |  | Milestone | bar: 2026-11-19
5.0 | SPRINT 5- Final Delivery & Showcase Preparation |  | 2026-11-24 | 2026-12-03 | 10 |  | Sprint | bar: 2026-11-24 to 2026-12-03
5.1 | Final Verification & Regression — US-01, 02, 11, 15, 28, 32, 33, 34 | Team | 2026-11-24 | 2026-12-01 | 8 | 4.12 | Sprint 5 | bar: 2026-11-24 to 2026-12-01
5.2 | Cleanup / QA / Evidence / Review / Buffer | Team | 2026-11-28 | 2026-12-03 | 6 | 5.1 | Sprint 5 | bar: 2026-11-28 to 2026-12-03
5.3 | Final Showcase | Team | 2026-12-05 | 2026-12-05 | 1 | 5.2 | Milestone | bar: 2026-12-05
5.4 | Final Paper + Sponsor Evaluation + PM Progress Report 5 | Ben / Team | 2026-12-13 | 2026-12-13 | 1 | 5.3 | Milestone | bar: 2026-12-13
| Scope Week Reference | Dates | Focus
| Week 1 | Sep 29–Oct 5 | Readiness / design
| Week 2 | Oct 6–12 | Network foundation
| Week 3 | Oct 13–19 | DHCP / DNS / NTP
| Week 4 | Oct 20–26 | RADIUS / AAA / SSH
| Week 5 | Oct 27–Nov 2 | ACLs / NAT-PAT / cross-training
| Week 6 | Nov 3–9 | Syslog / wireless / hardening
| Week 7 | Nov 10–16 | Integration / failure testing / non-author audit
| Week 8 | Nov 17–23 | Freeze / final regression / delivery prep
PM Report checkpoints document current progress and available evidence and do not necessarily represent sprint completion. Detailed subtasks, Main Owner QA responsibilities, and actual contributor records are maintained in Trello and are subject to change as meetings occur during implementation. US-12 and US-16 are shown as continuous bars because they are cross-cutting stories carried through every sprint per the Sprint Plan. WBS # and Dependencies (predecessor WBS #) added to reflect task sequencing; a task should not start until its listed predecessor(s) are functionally complete.